## Schedule
AI Upload Portal — MVP Schedule (Jun 15 – Aug 14, 2026)
Deadline: Aug 15 (Sat) → effective ship date Fri Aug 14. Resources: Praveer (80%) + Scott (support).
ID | Phase | Task | Owner | Start | End | Workdays | Gate | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10
1 | 0. Spec & Workflows | Kickoff: confirm MVP scope cut-list | Scott + Praveer | 2026-06-15 | 2026-06-15 | 1 |  | █
2 | 0. Spec & Workflows | Data spec: valid submission definition (CAD formats, PO/XLS schema, validation rules) | Scott | 2026-06-15 | 2026-06-18 | 4 |  | █
3 | 0. Spec & Workflows | Paper workflow mockups | Praveer | 2026-06-16 | 2026-06-19 | 4 |  | █
G0 | 0. Spec & Workflows | GATE 0: Data spec & workflows approved (Scott) | Scott | 2026-06-19 | 2026-06-19 | 1 | ◆ | ◆
4 | 1. Mock UI & Approval | Build mock UI | Praveer | 2026-06-22 | 2026-06-26 | 5 |  |  | █
5 | 1. Mock UI & Approval | Internal review of mock | Scott | 2026-06-25 | 2026-06-26 | 2 |  |  | █
6 | 1. Mock UI & Approval | Hamish & stakeholder review (book this meeting NOW) | Scott + Praveer | 2026-06-29 | 2026-06-29 | 1 |  |  |  | █
7 | 1. Mock UI & Approval | Revise mock from consolidated feedback (single round) | Praveer | 2026-06-30 | 2026-07-02 | 3 |  |  |  | █
G1 | 1. Mock UI & Approval | GATE 1: Design sign-off (Hamish) - build starts only after | Hamish | 2026-07-02 | 2026-07-02 | 1 | ◆ |  |  | ◆
8 | 2. Core Build | Scaffolding, hosting, invite-link auth | Praveer/Steve | 2026-07-06 | 2026-07-08 | 3 |  |  |  |  | █
9 | 2. Core Build | Multi-file upload flow | Praveer | 2026-07-08 | 2026-07-14 | 5 |  |  |  |  | █ | █
10 | 2. Core Build | Google Drive integration (folder structure, naming, metadata log) | Praveer/Steve | 2026-07-13 | 2026-07-16 | 4 | [5 empty] | █
11 | 2. Core Build | Deterministic validation (required files, CAD format, XLS schema) | Praveer | 2026-07-14 | 2026-07-17 | 4 | [5 empty] | █
G2 | 2. Core Build | GATE 2: End-to-end upload-to-Drive demo | Scott | 2026-07-17 | 2026-07-17 | 1 | ◆ |  |  |  |  | ◆
12 | 3. AI Guidance | AI guidance layer (explain failures, answer format questions, progress checklist) | Praveer | 2026-07-20 | 2026-07-28 | 7 | [6 empty] | █ | █
13 | 3. AI Guidance | Internal notifications (submission status emails) | Praveer | 2026-07-27 | 2026-07-29 | 3 | [7 empty] | █
14 | 3. AI Guidance | Internal E2E test with real cut plan data | Scott + Praveer | 2026-07-29 | 2026-07-31 | 3 | [7 empty] | █
G3 | 3. AI Guidance | GATE 3: Feature-complete demo (Hamish) | Hamish | 2026-07-31 | 2026-07-31 | 1 | ◆ | [6 empty] | ◆
15 | 4. Harden & Pilot | Bug fixes + security/access review (client IP protection) | Praveer | 2026-08-03 | 2026-08-06 | 4 | [8 empty] | █
16 | 4. Harden & Pilot | Friendly prospect pilot run | Scott | 2026-08-05 | 2026-08-11 | 5 | [8 empty] | █ | █
17 | 4. Harden & Pilot | Pilot fixes + runbook/docs | Praveer | 2026-08-10 | 2026-08-13 | 4 | [9 empty] | █
18 | 4. Harden & Pilot | Contingency buffer | Scott + Praveer | 2026-08-13 | 2026-08-14 | 2 | [9 empty] | █
G4 | 4. Harden & Pilot | GATE 4: MVP LAUNCH | Hamish | 2026-08-14 | 2026-08-14 | 1 | ◆ | [8 empty] | ◆
Key risks:
1. Stakeholder feedback loop slips past Jul 2 — every day of slip pushes launch. Book Hamish's demo (Jun 29) today; one consolidated feedback round only.
2. Data spec ambiguity — if 'valid submission' isn't machine-checkable by Gate 0, the AI guidance layer has nothing to enforce.
3. AI scope creep — MVP: deterministic checks + AI explanations. Not AI parsing of CAD geometry.
4. Real test data — source 2-3 genuine cut plan packages (CAD + PO) from existing clients by mid-July for the E2E test.
5. Client IP — prospects upload proprietary CAD designs; Drive access controls and a data handling note are MVP requirements, not nice-to-haves.